## a
Sprint	User Story	Microservice	Priority/Dependency
Sprint 1	As a user I want to register to the system so that I can access the application	Account & Authentication Manager / UI Manager	High - Base for access
Sprint 1	As a user I want to login into the system so that I can authenticate myself	Account & Authentication Manager / UI Manager	High - Depends on registration
Sprint 1	As a user I want to logout from the system so that I can exit the platform	Account & Authentication Manager / UI Manager	High - Base for session
Sprint 1	As a user I want to modify personal data so that I can keep my account updated	Account & Authentication Manager / UI Manager	Medium - Depends on login
Sprint 1	As a user I want to have a personal dashboard so that I can check my data	Account & Authentication Manager / UI Manager	Medium - Depends on login
Sprint 2	As an administrator I want to access a user dashboard so that I can manage accounts	Account & Authentication Manager / UI Manager	High - Depends on existing accounts
Sprint 2	As a driver I want to access my reputation score so I can know which parking spaces I can book	Account & Authentication Manager / UI Manager	Medium - Depends on existing accounts
Sprint 3	As a driver I want to search for available parking spots	Park Spot & Reservation Manager / Position/Notification Manager / UI Manager	High - Base for reservations
Sprint 3	As a driver I want to be able to search parking spots through filters	Park Spot & Reservation Manager / Position/Notification Manager / UI Manager	Medium - Depends on basic search
Sprint 3	As a driver I want to search for a parking spot selecting a keypoint and distance range	Park Spot & Reservation Manager / Position/Notification Manager / UI Manager	Medium - Depends on basic search
Sprint 4	As a driver I want to book a parking spot for a specific interval of time and pay for it	Park Spot & Reservation Manager / Payment Manager / Position/Notification Manager / UI Manager	High - Depends on parking search
Sprint 4	As a driver I want to choose the payment method so that I can pay	Payment Manager / UI Manager	High - Part of booking
Sprint 4	As a driver I want a visual confirmation of my payment request	Payment Manager / UI Manager	High - Depends on payment
Sprint 4	As a driver I want to receive the booking confirmation by email	Position/Notification Manager / UI Manager	Medium - Depends on booking
Sprint 5	As a driver I want to be able to delete a reservation	Park Spot & Reservation Manager / UI Manager	Medium - Depends on booking
Sprint 5	As a driver I want to see a visual confirmation of the cancellation	UI Manager	Medium - Depends on cancellation
Sprint 5	As a driver I want to receive the details of the resident after a booking	Position/Notification Manager / UI Manager	Medium - Depends on booking
Sprint 6	As a driver I want to rate the parking service	Park Spot & Reservation Manager / UI Manager	Medium - Depends on completed booking
Sprint 6	As a driver I want to be notified when a parking is available near me	Position/Notification Manager / UI Manager	Medium - Requires updated location
Sprint 7	As a resident I want to insert into the system my parking space	Park Spot & Reservation Manager / UI Manager	High - Base for sharing parking spots
Sprint 7	As a resident I want to assign labels to my parking spots	Park Spot & Reservation Manager / UI Manager	Medium - Depends on inserted parking spots
Sprint 7	As a resident I want a real-time parking spot dashboard	Park Spot & Reservation Manager / UI Manager	Medium - Depends on inserted parking spots
Sprint 7	As a resident I want to change the status of the parking spot	Park Spot & Reservation Manager / UI Manager	Medium - Depends on inserted parking spots
Sprint 8	As a resident I want to delete a reservation	Park Spot & Reservation Manager / UI Manager	Medium - Depends on driver bookings
Sprint 8	As a resident I want to set a reputation threshold for reserving a parking spot	Park Spot & Reservation Manager / UI Manager	Medium - Depends on driver reputation system
Sprint 8	As a resident I want to have a booking queue for my parking spot	Park Spot & Reservation Manager / UI Manager	Medium - Depends on reputation threshold
Sprint 8	As a resident I want to receive notifications when a driver asks for a booking	Position/Notification Manager / UI Manager	Medium - Depends on booking requests
Sprint 9	As a resident I want to rate the driver	Park Spot & Reservation Manager / UI Manager	Medium - Depends on completed driver bookings