## EXAMPLE Gantt Chart & Burndown
	SCRUM PROJECT MANAGEMENT GANTT CHART					https://goo.gl/ejIdKR
	GANTT CHART AND BURNDOWN
				SPRINTS	SPRINT 1
				SPRINT 2
				SPRINT 3
				SPRINT 4
				SPRINT 5
	WORK BREAKDOWN STRUCTURE	TASK TITLE	TASK OWNER	AMOUNT OF WORK IN HOURS			SPRINT	START DATE	DUE DATE	DURATION	PCT OF TASK COMPLETE	WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12
				ESTIMATE	COMPLETED	REMAINING					M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
	1	Project Conception and Initiation		309	309	0					100%
	1,1	Project Charter	Leon W	40	40	0		12/03/2017	15/03/2017	4	100%
	1.1.1	Project Charter Revisions	Kylie R	25	25	0		15/03/2017	16/03/2017	2	100%
	1,2	Research	Pete S	100	100	0		15/03/2017	21/03/2017	7	100%
	1,3	Projections	Steve L	60	60	0		16/03/2017	22/03/2017	7	100%
	1,4	Stakeholders	Allen W	40	40	0		17/03/2017	22/03/2017	6	100%
	1,5	Guidelines	Malik M	32	32	0		18/03/2017	22/03/2017	5	100%
	1,6	Project Initiation	Malik M	12	12	0		23/03/2017	23/03/2017	1	100%
	2	Project Definition and Planning		210	110	100					52%
	2,1	Scope and Goal Setting	Steve L	80	70	10		24/03/2017	28/03/2017	5	88%
	2,2	Budget	Allen W	60	40	20		29/03/2017	02/04/2017	5	67%
	2,3	Communication Plan	Malik M	40	0	40				1	0%
	2,4	Risk Management	Malik M	30	0	30				1	0%
	3	Project Launch and Execution		66	0	66					0%
	3,1	Status and Tracking	Pete S	20	0	20				1	0%
	3,2	KPIs	Leon W	20	0	20				1	0%
	3.2.1	Monitoring	Kylie R	8	0	8				1	0%
	3.2.2	Forecasts	Kylie R	12	0	12				1	0%
	3,3	Project Updates	Pete S	4	0	4				1	0%
	3.3.1	Chart Updates	Malik M	2	0	2				1	0%
	4	Project Performance/Monitoring		32	0	32					0%
	4,1	Project Objectives	Steve L	8	0	8				1	0%
	4,2	Quality Deliverables	Allen W	12	0	12				1	0%
	4,3	Effort and Cost Tracking	Malik M	8	0	8				1	0%
	4.4	Project Performance	Malik M	4	0	4				1	0%
				ESTIMATE	COMPLETED	REMAINING	DAYS	EST/DAYS
		BURNDOWN DATA	TOTAL HOURS	617	419	198	60	10,2833333333333			DAY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60		TOTAL HOURS
				^ Enter number of days				PLAN	617	607	596	586	576	566	555	545	535	524	514	504	494	483	473	463	452	442	432	422	411	401	391	380	370	360	350	339	329	319	309	298	288	278	267	257	247	237	226	216	206	195	185	175	165	154	144	134	123	113	103	93	82	72	62	51	41	31	21	10
				ESTIMATE	617	609	589	559	519	499	488	472	430	385	365	355	339	315	267	247	243	238	234	226	218	213	208	203	200	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198		15968
				Enter hours completed per day ---->	HRS COMPLETED	8	20	30	40	20	11	16	42	45	20	10	16	24	48	20	4	5	4	8	8	5	5	5	3	2					419
				HRS REMAINING	609	589	559	519	499	488	472	430	385	365	355	339	315	267	247	243	238	234	226	218	213	208	203	200	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198	198		15549
BURNDOWN CHART

	CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## BLANK Gantt Chart & Burndown
	SCRUM PROJECT MANAGEMENT GANTT CHART
	GANTT CHART AND BURNDOWN
						SPRINTS	SPRINT 1
						SPRINT 2
						SPRINT 3
						SPRINT 4
						SPRINT 5
	WORK BREAKDOWN STRUCTURE	TASK TITLE	TASK OWNER	AMOUNT OF WORK IN HOURS			SPRINT	START DATE	DUE DATE	DURATION	PCT OF TASK COMPLETE	WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12
				ESTIMATE	COMPLETED	REMAINING					M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
	1			0	0	0					#DIV/0!
	1,1					0				1	#DIV/0!
	1.1.1					0				1	#DIV/0!
	1,2					0				1	#DIV/0!
	1,3					0				1	#DIV/0!
	1,4					0				1	#DIV/0!
	1,5					0				1	#DIV/0!
	1,6					0				1	#DIV/0!
	2			0	0	0					#DIV/0!
	2,1					0				1	#DIV/0!
	2,2					0				1	#DIV/0!
	2,3					0				1	#DIV/0!
	2,4					0				1	#DIV/0!
	3			0	0	0					#DIV/0!
	3,1					0				1	#DIV/0!
	3,2					0				1	#DIV/0!
	3.2.1					0				1	#DIV/0!
	3.2.2					0				1	#DIV/0!
	3,3					0				1	#DIV/0!
	3.3.1					0				1	#DIV/0!
	4			0	0	0					#DIV/0!
	4,1					0				1	#DIV/0!
	4,2					0				1	#DIV/0!
	4,3					0				1	#DIV/0!
	4.4					0				1	#DIV/0!
				ESTIMATE	COMPLETED	REMAINING	DAYS	EST/DAYS
		BURNDOWN DATA	TOTAL HOURS	0	0	0	60	0			DAY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60		TOTAL HOURS
						^ Enter number of days				PLAN	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
						ESTIMATE	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
						Enter hours completed per day ---->	HRS COMPLETED					0
						HRS REMAINING	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
BURNDOWN CHART

				CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY	SPRINT	FUNCTIONALITY	TASK TITLE	TASK DESCRIPTION	TASK OWNER	WORK ESTIMATE IN HOURS	STATUS	NOTES		STATUS KEY		WORK ESTIMATE IN HOURS
					1	Not Started			Not Started		1
					2	In Progress			In Progress		2
					8	Completed			Completed		4
					8	Not Started					8
					4					16
					80					24
					16					40
					8					80
					4
					2
					24
					40
					8

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE	TASK DESCRIPTION	ADDED BY	DATED ADDED