## BLANK_Gantt_Chart_&_Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
					SPRINTS	SPRINT 1
					SPRINT 2
					SPRINT 3
					SPRINT 4
					SPRINT 5
WORK BREAKDOWN STRUCTURE	TASK TITLE	TASK OWNER	AMOUNT OF WORK IN HOURS			SPRINT	START DATE	DUE DATE	DURATION	PCT OF TASK COMPLETE	WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12
			ESTIMATE	COMPLETED	REMAINING					M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
1	Documentation Managment		45	47	-2		01/10/2025	07/10/2025		104%
1.1	Repository setup and basic project structure	All	6	6	0		01/10/2025	02/10/2025	2	100%
1.2	Requirements Gathering	All	4	6	-2		02/10/2025	02/10/2025	1	150%
1.3	User stories definition	All	8	8	0		02/10/2025	02/10/2025	1	100%
1.4	Mockups creation	Serena & Federico	8	8	0		03/10/2025	06/10/2025	4	100%
1.5	Function point & CoCoMo estimation	Pierluca	8	9	-1		03/10/2025	06/10/2025	4	113%
1.6	Microservices Architecture Design	Valerio & Matteo	8	8	0		03/10/2025	06/10/2025	4	100%
1.7	Documentation Revision	All	3	2	1		07/10/2025	07/10/2025	1	67%
2	Account managment		40	39	1		08/10/2025	15/10/2025		98%
2.1	DB setup	Matteo	8	8	0		08/10/2025	09/10/2025	2	100%
2.2	Implementation of user registration	Valerio	8	6	2		10/10/2025	13/10/2025	4	75%
2.3	Implementation of Login / Logout	Pierluca	8	8	0		13/10/2025	13/10/2025	1	100%
2.4	User Data modification	Federico	8	9	-1		13/10/2025	14/10/2025	2	113%
2.5	Basic Dashboard Visualization	Serena	8	8	0		13/10/2025	15/10/2025	3	100%
3	Resident Functionalities (Backend - Frontend)		40	37	3		16/10/2025	22/10/2025		93%
3.1	Interface implementation to add parking spot	Serena	6	5	1		16/10/2025	16/10/2025	1	83%
3.2	Backend to add a parking spot	Valerio	8	8	0		17/10/2025	20/10/2025	4	100%
3.3	Implementation of adding availability time slots and labels	Valerio	6	6	0		17/10/2025	20/10/2025	4	100%
3.4	Implementation of real time parking spot dashboard for residents	Matteo	8	8	0		20/10/2025	21/10/2025	2	100%
3.5	Interface to add time slot availabilities	Federico	6	4	2		17/10/2025	20/10/2025	4	67%
3.6	Parking spot dashboard interface	Pierluca	6	6	0		20/10/2025	22/10/2025	3	100%
4	Parking Search		40	40	0		23/10/2025	30/10/2025		100%
4.1	Search parking spot backend	Matteo	8	8	0		23/10/2025	24/10/2025	2	100%
4.2	Interface to search parking spot	Pierluca	8	8	0		23/10/2025	24/10/2025	2	100%
4.3	Filter search implementation	Federico	8	8	0		24/10/2025	27/10/2025	4	100%
4.4	Distance range implementation	Serena	8	8	0		24/10/2025	27/10/2025	4	100%
4.5	User homepage interface	Valerio	8	8	0		28/10/2025	30/10/2025	3	100%
5	Booking and Payment Systems		120	122	-2		03/11/2025	17/11/2025		102%
5.1	Implementation of map view to see near parking spots	Matteo	16	16	0		03/11/2025	05/11/2025	3	100%
5.2	Booking backend	Pierluca & Federico	24	24	0		03/10/2025	06/10/2025	4	100%
5.3	Parking spots booking interface	Serena	8	8	0		03/11/2025	05/11/2025	3	100%
5.4	Resident reservation request queue implementation	Serena	8	10	-2		05/11/2025	07/11/2025	3	125%
5.5	Driver's details in reservation request	Valerio	8	8	0		07/11/2025	10/11/2025	4	100%
5.6	Reservation request queue page	Federico	8	8	0		07/11/2025	10/11/2025	4	100%
5.7	Cancellation of reservation request	Matteo	8	9	-1		10/11/2025	12/11/2025	3	113%
5.8	Interface for a driver's booking requests	Pierluca	8	7	1		10/11/2025	12/11/2025	3	88%
5.9	Personal calendar view implementation for parking spots availability and bookings	Serena	8	8	0		11/11/2025	13/11/2025	3	100%
5.10	Backend for calendar view	Matteo	8	8	0		13/11/2025	14/11/2025	2	100%
5.11	Payment system backend	Valerio & Matteo	16	16	0		13/11/2025	17/11/2025	5	100%
6	Notification System		80	80	0		18/11/2025	27/11/2025		100%
6.1	Email notifcation templates	Serena	8	8	0		18/11/2025	18/11/2025	1	100%
6.2	Notification implementation after user's registration	Serena & Matteo	12	12	0		19/11/2025	21/11/2025	3	100%
6.3	Notification implementation for new booking request from a driver	Valerio	12	12	0		20/11/2025	21/11/2025	2	100%
6.4	Notification implementation for booking confirmation from resident	Federico	12	12	0		21/11/2025	24/11/2025	4	100%
6.5	Notification implementation for rejected booking request	Pierluca	12	12	0		24/11/2025	25/11/2025	2	100%
6.6	Notification implementation for an available parking spot near driver's position	Valerio	12	12	0		21/11/2025	25/11/2025	5	100%
6.7	Notification implementation for cancelled booking request	Matteo	12	12	0		26/11/2025	27/11/2025	2	100%
7	Reputation and Rating systems		52	50	2		28/11/2025	05/12/2025		96%
7.1	Added section to leave a review to a resident	Federico	7	7	0		28/11/2025	28/11/2025	1	100%
7.2	Added section to leave a review to a driver	Serena	7	7	0		28/11/2025	28/11/2025	1	100%
7.3	Reviews and rates backend	Valerio & Matteo	12	10	2		01/12/2025	02/12/2025	2	83%
7.4	Implementation of section to read reviews from other users on personal dashboard	Pierluca	6	6	0		03/12/2025	04/12/2025	2	100%
7.5	Notification template for received review and rating	Serena	6	6	0		04/12/2025	04/12/2025	1	100%
7.6	Notification implementation for received review and rating	Matteo	8	8	0		04/12/2025	05/12/2025	2	100%
7.7	Statistics added to user dashboard	Valerio	6	6	0		04/12/2025	05/12/2025	2	100%
8	Admin Functionalities		35	35	0		09/12/2025	12/12/2025		100%
8.1	Creation of Admin dashboard to monitor the system	Pierluca	6	6	0		09/12/2025	09/12/2025	1	100%
8.2	Creation of admin dashboard to view and search users	Federico	4	4	0		09/12/2025	10/12/2025	2	100%
8.3	Implementation of users' search	Matteo	6	6	0		09/12/2025	10/12/2025	2	100%
8.4	Creation of interface to view user details and manage their account	Serena	6	6	0		12/12/2025	12/12/2025	1	100%
8.5	Implementation of user account enable/disable functionality	Valerio	7	7	0		11/12/2025	12/12/2025	2	100%
8.6	Notifcation to user when enabling/disabling account	Matteo	6	6	0		11/12/2025	12/12/2025	2	100%

BURNDOWN DATA			ESTIMATE	COMPLETED	REMAINING	DAYS	EST/DAYS
		TOTAL HOURS	452	450	2	60	7,533333333
					DAY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60
					PLAN	452	444	437	429	422	414	407	399	392	384	377	369	362	354	347	339	331	324	316	309	301	294	286	279	271	264	256	249	241	234	226	218	211	203	196	188	181	173	166	158	151	143	136	128	121	113	105	98	90	83	75	68	60	53	45	38	30	23	15	8
					ESTIMATE	452	449	433	421	409	407	403	399	396	379	370	366	361	352	338	333	331	323	307	299	296	294	291	291	277	264	249	239	227	213	200	192	180	171	166	158	154	146	142	132	114	104	94	88	82	68	63	58	55	39	32	32	21	16	9	-3	-3	-3	-3	-3
					HRS COMPLETED	3	16	12	12	2	4	4	3	17	9	4	5	9	14	5	2	8	16	8	3	2	3		14	13	15	10	12	14	13	8	12	9	5	8	4	8	4	10	18	10	10	6	6	14	5	5	3	16	7		11	5	7	12
					HRS REMAINING	449	433	421	409	407	403	399	396	379	370	366	361	352	338	333	331	323	307	299	296	294	291	291	277	264	249	239	227	213	200	192	180	171	166	158	154	146	142	132	114	104	94	88	82	68	63	58	55	39	32	32	21	16	9	-3	-3	-3	-3	-3	-3

				BURNDOWN CHART

## Release_Backlog
				SCRUM PROJECT MANAGEMENT GANTT CHART
				RELEASE BACKLOG
PRIORITY	SPRINT	FUNCTIONALITY	TASK TITLE	TASK DESCRIPTION	TASK OWNER	WORK ESTIMATE IN HOURS	STATUS	NOTES		STATUS KEY		WORK ESTIMATE IN HOURS
High	2	Accoun Managment	Registration	As a user I want to register to the system so that I can access to the application.	All	8	Completed			Not Started		1
High	2		Login	As a user I want to login into the system so that I can authenticate myself to the platform and use app’s functionalities.	All	8	Completed			Completed		2
High	2		Logout	As a user I want to logout from the system so that I can exit from the platform while I don’t use it.	All	8	Completed					4
Low	2		Edit Profile	As a user I want to modify personal data so that I can keep updated my account.	All	8	Completed					6
High	2		Dashboard visualization	As a user I want to have a personal dashboard so that I can check my personal data and history.	All	6	Completed					7
High	3	Resident Functionalities	Adding parking spot	As a resident I want to insert into the system my parking space so that I can share it with other users and gain revenues.	All	10	Completed					8
High	3		Labels assignment	As a resident I want to assign labels to my parking spots so that drivers can easily search for them.	All	10	Completed					10
High	3		Resident parking spot list	As a resident I want to view a list of all my parking spots and add availability time slots, so I can decide when each spot can be booked by the drivers.	All	8	Completed					12
Medium	4	Parking Search and Driver's Functionalities	User Homepage	As a user I want to see all the functionalities of the app in my homepage so that I can access easily to them.	All	8	Completed					16
High	4		Parking Spot Search	As a driver I want to search for available parking spots so that I can book it.	All	12	Completed					24
High	4		Filters Search	As a driver I want to be able to search parking spots through filters so that I can find the best parking for my needs.	All	8	Completed
High	4		Distance range Search	As a driver I want to search for a parking spot selecting a distance range so that I can find the parking space in the best possible position.	All	8	Completed
High	4		Available Parking Spot list	As a driver I want to see all parking spots available when I search for them, in order to decide myself which I want to book.	All	8	Completed
High	5	Booking and payment systems	Parking Spot Requests List	As a resident I want to view all booking requests for my parking spots so that I can choose which drivers to authorize for each specific spot and time slot.	All	8	Completed
High	5		Driver's Details preview	As a resident I want to see driver's details and reviews in a request so that I can choose if accept the request.	All	8	Completed
High	4		Time slot Booking and payment	As a driver I want to book a parking spot for a specific interval of time and pay for it so that I can easily park my car.	All	24	Completed
High	5		Request Rejection	As a resident I want to reject a reservation request so that I can have the full control of my parking spaces.	All	8	Completed
Medium	5		Parking Spot Map	As a driver I want a map in the homepage that displays all the available parking spots so that I can precisely choose the parking spot position.	All	16	Completed
Medium	5		Payment Method	As a driver I want to choose the payment method so that I can pay the parking spot in several digital ways.	All	16	Completed
Medium	5		Driver's Reservation Requests list	As a driver I want to see the list of all my reservations requests, so that I can see which are still waiting to be accepted by the resident and which have been already accepted or rejected.	All	8	Completed
Medium	5		Reservation Request Deletion	As a driver I want to be able to delete a reservation request so that I can free a parking spot if I don’t need it anymore.	All	8	Completed
Low	5		Calendar View	As a user I want to see all my bookings and/or my parking spots in a calendar view, so I can quickly understand my schedule and have a clear overview of my reservations.	All	8	Completed
Medium	6	Notification System	Registration Mail	As a user I want to receive a confirmation mail after I registered so that I know that all has gone fine.	All	12	Completed
Medium	6		Available Near Parking Spot Mail	As a driver I want to receive a notifcation when there is a free parking spot near my current position so I can book it if I need it	All	12	Completed
Medium	6		Rejected Request Mail	As a driver I want to receive a notification when a resident rejects my request, so I can know whether I have to book another parking spot.	All	12	Completed
Medium	6		Account Status Switch Mail	As a user I want to receive a notification if my account has been disabled or enabled by administrators so that I know if I can use the app.	All	12	Completed
Medium	6		Booking Confirmation Mail	As a driver I want to receive the booking confirmation by email when the resident accepts my request, so that I can check the reservation details.	All	12	Completed
Medium	6		Booking Request Mail	As a resident I want to receive notifications when a driver asks for a booking so that I’m informed about it.	All	12	Completed
Medium	6		Resident Details Mail	As a driver I want to receive the details of the resident after a booking so that I can contact them if needed.	All	12	Completed
Medium	6		Deleted Request Mail	As a resident I want to receive a notification if a driver cancels their booking request on my parking spot, so I can be updated in real time about the demand for my parking spots.	All	12	Completed
Medium	7	Reputation and rating System	Reviewing a Resident Service	As a driver I want to comment the parking service so that I can share my parking experience with other drivers.	All	7	Completed
Medium	7		Reputation Score on dashboard	As a driver I want to access my reputation score on my dashboard so I can know which parking spaces I can book.	All	7	Completed
Medium	7		Resident received reviews on dashboard	As a resident I want to see all the reviews I have received from the drivers so that I can evaluate my behaviour.	All	6	Completed
Medium	7		Rating Resident Service	As a driver, I want to rate the resident whose parking spot I booked, so that I can share my experience.	All	12	Completed
Medium	7		Reputation Threshold on Parking Spot	As a resident I want to set a reputation treshold to reserve a parking spot, so that I can give priority to higher reputation users.	All	6	Completed
Medium	7		Rating a Driver	As a resident I want to rate a driver that used one of my parking spots, so that I can share the related experience.	All	8	Completed
Low	7		Review Notification	As a user I want to receive a notifcation when other users leave me reviews and ratings so I can check immediately how was their experience.	All	8	Completed
Low	7		Personal Statitistic	As user I want to see my statistics in the personal dashboard, so I can know the number of my active reservations, my available parking spots and more.	All	6	Completed
Low	7		Personal Reviews and Rating Visualization	As a driver I want to see all the reviews I have received from the residents so that I can evaluate my behaviour.	All	6	Completed
Low	8	Admin Functionalities	System Status Visualization	As an administrator I want to be able to visualize the status of my application's microservices, so I know if there are some problems.	All	12	Completed
Low	8		Users Search	As an administrator I want to view all the users and search for them so I can manage their accounts.	All	12	Completed
Low	8		Users' Information Visualization	As an administrator I want to have access to a user’s information so I can decide to disable or enable their account.	All	12	Completed

## User_Stories_or_Tasks
	SCRUM PROJECT MANAGEMENT GANTT CHART
	USER STORIES or TASKS
#	TASK TITLE	AS A	I WANT TO	SO THAT I CAN	ADDED BY	DATED ADDED
1	Registration	User	register to the system	access to the application	All	02/10/2025
2	Login	User	logint into the system	authenticate myself to the platform and use the application functionalities	All	02/10/2025
3	Logout	User	logoutt from the system	exit from the platform while I don't use it	All	02/10/2025
4	Edit Profile	User	modify personal data	keep updated my account	All	02/10/2025
5	Dashboard visualization	User	have a personal dashboard	check my personal data and history	All	02/10/2025
6	Adding parking spot	Resident	insert into the system my parkin space	share it with others and gain revenues	All	02/10/2025
7	Labels assignment	Resident	assign labels to my parking spots	easily search for them	All	02/10/2025
8	Resident parking spot list	Resident	view a list of all my parking spots and add availability time slots	decide when each spot can be booked by the drivers	All	02/10/2025
9	User Homepage	User	see all functionalites of the app in my homepage	access easily to them	All	02/10/2025
10	Parking Spot Search	Driver	search for available parking spot	book it	All	02/10/2025
11	Filters Search	Driver	be able to searchparking spots through filters	find the best parking for my needs	All	02/10/2025
12	Distance range Search	Driver	search for a parking spot selecting a distance range	find the parking space in the best possible position	All	02/10/2025
13	Time slot Booking	Driver	book a parking spot for a specific interval of time and pay for it	easily park my car	All	02/10/2025
14	Available Parking Spot list	Driver	available parking spot when I search for them	decide myself which I want to book	All	02/10/2025
15	Parking Spot Requests List	Resident	view all booking requests for my parking spots	choose which druvers to authorize for each specific spot and time slot	All	02/10/2025
16	Driver's Details preview	Resident	see a driver's details and reviews in a request	choose to accept the request	All	02/10/2025
17	Request Rejection	Resident	reject a reservation request	have the full control of my parking spaces	All	02/10/2025
18	Parking Spot Map	Driver	a map in the homepage that displays all the available parking spots	precisely choose the parking spot position	All	02/10/2025
19	Payment Method	Driver	choose the payment method	pay the parking spot in several digital ways	All	02/10/2025
20	Driver's Reservation Requests list	Driver	see the list of all my reservations requests	see which are still waiting to be accepted by the resident and which have beenalready accepted or rejected	All	02/10/2025
21	Reservation Request Deletion	Driver	delete a reservation request	free a parking spot if I don't nedd it anymore	All	02/10/2025
22	Calendar View	User	see all my bookings and/or my parking spots in a calendar view	quickly understand my schedule and have a clear overview of my reservations	All	02/10/2025
23	Registration Mail	User	receive a confirmation mail after I registered	know that all has gone fine	All	02/10/2025
24	Available Near Parking Spot Mail	Driver	receive a notifcation when there is a free parking spot near my current position	book it if I need it		02/10/2025
25	Rejected Request Mail	Driver	receive a notification when a resident rejects my request	know whether I have to book another parking spot	All	02/10/2025
26	Account Status Switch Mail	User	receive a notification if my account has been disabled or enabled by administrators	know if I can use the app	All	02/10/2025
27	Booking Confirmation Mail	Driver	booking confirmation mailt the booking confirmation	check the reservation details	All	02/10/2025
28	Booking Request Mail	Resident	receive the booking confirmation by email when the resident accepts my request	be aware of it	All	02/10/2025
29	Resident Details Mail	Driver	receive the details of the resident after a booking	contact thekm if I need to	All	02/10/2025
30	Deleted Request Mail	Resident	receive a notification if a driver cancels their booking request on my parking spot	be updated in real time about the demand for my parking spots	All	02/10/2025
31	Reviewing a Resident Service	Driver	comment the parking service	share my parking experience with other dirver	All	02/10/2025
32	Reputation Score on dashboard	Driver	access my reputation score on my dashboard	know which parking spaces I can book.	All	02/10/2025
33	Resident received reviews on dashboard	Resident	see all the reviews I have received from the drivers	evaluate my behavior	All	02/10/2025
34	Rating Resident Service	Driver	rate the resident whose parking spot I booked	share my experience	All	02/10/2025
35	Reputation Threshold on Parking Spot	Resident	set a reputation treshold to reserve a parking spot	give priority to higher reputation users	All	02/10/2025
36	Rating a Driver	Resident	rate a driver that used one of my parking spots	share the related experience	All	02/10/2025
37	Personal Statitistic	User	see my statistics in the personal dashboard	know the number of my active reservations	All	02/10/2025
38	Personal Reviews and Rating Visualization	Driver	see all the reviews I have received from the drivers	know the number of my active reservations, my available parking spots and more	All	02/10/2025
39	Review Notification	User	receive a notifcation when other users leave me reviews and ratings	check immediately how was their experience	All	02/10/2025
40	System Status Visualization	Administrator	be able to visualize the status of my application's microservices	know if there are some problems	All	02/10/2025
41	Users Search	Administrator	to view all the users and search for them	manage their accounts	All	02/10/2025
42	Users' Information Visualization	Administrator	have access to a user's information	decide to disable or enable their account	All	02/10/2025