## EXAMPLE_Gantt_Chart_&_Burndown
	SCRUM PROJECT MANAGEMENT GANTT CHART					https://goo.gl/ejIdKR
	GANTT CHART AND BURNDOWN
				SPRINTS	SPRINT 1
				SPRINT 2
				SPRINT 3
				SPRINT 4
				SPRINT 5
	WORK BREAKDOWN STRUCTURE	TASK TITLE	TASK OWNER	AMOUNT OF WORK IN HOURS			SPRINT	START DATE	DUE DATE	DURATION	PCT OF TASK COMPLETE	WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12
				ESTIMATE	COMPLETED	REMAINING					M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
	1	Sprint 1		0	0	0					#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
	2	Sprint 2		0	0	0					#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
	3	Sprint 3		0	0	0					#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
	4	Sprint 4		0	0	0					#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
	5	Sprint 5		0	0	0					#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				0				1	#DIV/0!
				ESTIMATE	COMPLETED	REMAINING	DAYS	EST/DAYS
		BURNDOWN DATA	TOTAL HOURS	0	0	0	60	0			DAY	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60		TOTAL HOURS
				^ Enter number of days				PLAN	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
				ESTIMATE	0	-8	-28	-58	-98	-118	-129	-145	-187	-232	-252	-262	-278	-302	-350	-370	-374	-379	-383	-391	-399	-404	-409	-414	-417	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419		-21052
				Enter hours completed per day ---->	HRS COMPLETED	8	20	30	40	20	11	16	42	45	20	10	16	24	48	20	4	5	4	8	8	5	5	5	3	2					419
				HRS REMAINING	-8	-28	-58	-98	-118	-129	-145	-187	-232	-252	-262	-278	-302	-350	-370	-374	-379	-383	-391	-399	-404	-409	-414	-417	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419	-419		-21471
BURNDOWN CHART

	CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## BLANK_Gantt_Chart_&_Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
					SPRINTS	SPRINT 1
					SPRINT 2
					SPRINT 3
					SPRINT 4
					SPRINT 5
WORK BREAKDOWN STRUCTURE	TASK TITLE	TASK OWNER	AMOUNT OF WORK IN HOURS			SPRINT	START DATE	DUE DATE	DURATION	PCT OF TASK COMPLETE	WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12
			ESTIMATE	COMPLETED	REMAINING					M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
1	Documentation Managment		43	45	-2		01/10/2025	07/10/2025		105%
1.1	Repository setup and basic project structure	All	4	4	0		01/10/2025	02/10/2025	2	100%
1.2	Requirements Gathering	All	4	6	-2		02/10/2025	02/10/2025	1	150%
1.3	User stories definition	All	8	8	0		02/10/2025	02/10/2025	1	100%
1.4	Mockups creation	Serena & Federico	8	8	0		03/10/2025	05/10/2025	3	100%
1.5	Function point & CoCoMo estimation	Pierluca	8	9	-1		03/10/2025	05/10/2025	3	113%
1.6	Microservices Architecture Design	Valerio & Matteo	8	8	0		04/10/2025	06/10/2025	3	100%
1.7	Documentation Revision	All	3	2	1		07/10/2025	07/10/2025	1	67%
2	Account managment and admin dashboard		40	40	0		08/10/2025	15/10/2025		100%
2.1	DB setup	Matteo	8	8	0		08/10/2025	09/10/2025	2	100%
2.2	Implementation of user registration	Valerio	8	8	0		10/10/2025	11/10/2025	2	100%
2.3	Implementation of Login / Logout	Pierluca	8	8	0		11/10/2025	12/10/2025	2	100%
2.4	User Data modification	Federico	8	8	0		12/10/2025	13/10/2025	2	100%
2.5	Basic Dashboard Visualization	Serena	8	8	0		10/10/2025	14/10/2025	5	100%
3	Resident Functionalities (Backend - Frontend)		40	37	3		15/10/2025	22/10/2025		93%
3.1	Interface implementation to add parking spot	Serena	6	5	1		15/10/2025	15/10/2025	1	83%
3.2	Backend to add a parking spot	Valerio	8	8	0		16/10/2025	17/10/2025	2	100%
3.3	Implementation of adding availability time slots	Valerio	6	6	0		17/10/2025	18/10/2025	2	100%
3.4	Implementation of real time parking spot dashboard for residents	Matteo	8	8	0		18/10/2025	19/10/2025	2	100%
3.5	Interface to add time slot availabilities	Federico	6	4	2		17/10/2025	19/10/2025	3	67%
3.6	Parking spot dashboard interface	Pierluca	6	6	0		20/10/2025	22/10/2025	3	100%
4	Parking Search		40	40	0		23/10/2025	30/10/2025		100%
4.1	Search parking spot backend	Matteo	8	8	0		23/10/2025	24/10/2025	2	100%
4.2	Interface to search parking spot	Pierluca	8	8	0		23/10/2025	24/10/2025	2	100%
4.3	Filter search implementation	Federico	8	8	0		24/10/2025	25/10/2025	2	100%
4.4	Distance range implementation	Serena	8	8	0		24/10/2025	25/10/2025	2	100%
4.5	User homepage interface	Valerio	8	8	0		25/10/2025	27/10/2025	3	100%
5	Booking and Payment Systems		120	122	-2		03/11/2025	17/11/2025		102%
5.1	Implementation of map view to see near parking spots	Matteo	16	16	0		03/11/2025	05/11/2025	3	100%
5.2	Booking backend	Pierluca & Federico	24	24	0		03/10/2025	06/10/2025	4	100%
5.3	Parking spots booking interface	Serena	8	8	0		03/11/2025	05/11/2025	3	100%
5.4	Resident reservation request queue implementation	Serena	8	10	-2		05/11/2025	07/11/2025	3	125%
5.5	Driver's details in reservation request	Valerio	8	8	0		07/11/2025	08/11/2025	2	100%
5.6	Reservation request queue page	Federico	8	8	0		07/11/2025	09/11/2025	3	100%
5.7	Cancellation of reservation request	Matteo	8	9	-1		09/11/2025	10/11/2025	2	113%
5.8	Interface for a driver's booking requests	Pierluca	8	7	1		09/11/2025	10/11/2025	2	88%
5.9	Personal calendar view implementation for parking spots availability and bookings	Serena	8	8	0		11/11/2025	13/11/2025	3	100%
5.10	Backend for calendar view	Matteo	8	8	0		13/11/2025	15/11/2025	3	100%
5.11	Payment system backend	Valerio & Matteo	16	16	0		13/11/2025	17/11/2025	5	100%
6	Notification System		80	78	2		18/11/2025	28/11/2025	11	98%
6.1	Email notifcation templates	Serena	8	8	0		18/11/2025	18/11/2025	1	100%
6.2	Notification implementation after user's registration	Serena & Matteo	12	10	2		19/11/2025	21/11/2025	3	83%
6.3	Notification implementation for new booking request from a driver	Valerio	12	12	0		20/11/2025	21/11/2025	2	100%
6.4	Notification implementation for booking confirmation from resident	Federico	12	12	0		21/11/2025	22/11/2025	2	100%
6.5	Notification implementation for rejected booking request	Pierluca	12	12	0		23/11/2025	24/11/2025	2	100%
6.6	Notification implementation for an available parking spot near driver's position	Valerio	12	12	0		23/11/2025	25/11/2025	3	100%
6.7	Notification implementation for cancelled booking request	Matteo	12	12	0		26/11/2025	27/11/2025	2	100%
7	Reputation and Rating systems		40	42	-2		29/11/2025	06/12/2025	8	105%
7.1	Added section to leave a review to a resident	Federico	7	7	0		29/11/2025	29/11/2025	1	100%
7.2	Added section to leave a review to a driver	Serena	7	7	0		29/11/2025	29/11/2025	1	100%
7.3	Reviews and rates backend	Valerio & Matteo	12	14	-2		30/11/2025	02/12/2025	3	117%
7.4	Implementation of section to read reviews from other users on personal dashboard	Pierluca	7	7	0		03/12/2025	04/12/2025	2	100%
7.5	Statistics added to user dashboard	Serena	7	7	0		05/12/2025	06/12/2025	2	100%
8	Admin Functionalities		48	48	0		07/12/2025	16/12/2025	10	100%
8.1	Creation of Admin dashboard to monitor the system	Pierluca	8	8	0		07/12/2025	09/12/2025	3	100%
8.2	Creation of admin dashboard to view and search users	Federico	8	8	0		07/12/2025	09/12/2025	3	100%
8.3	Implementation of users' search	Matteo	8	8	0		09/12/2025	11/12/2025	3	100%
8.4	Creation of interface to view user details and manage their account	Serena	8	8	0		12/12/2025	13/12/2025	2	100%
8.5	Implementation of user account enable/disable functionality	Valerio	8	8	0		14/12/2025	15/12/2025	2	100%
8.6	Notifcation to user when enabling/disabling account	Matteo	8	8	0		15/12/2025	16/12/2025	2	100%
		BURNDOWN CHART

			CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release_Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY	SPRINT	FUNCTIONALITY	TASK TITLE	TASK DESCRIPTION	TASK OWNER	WORK ESTIMATE IN HOURS	STATUS	NOTES		STATUS KEY		WORK ESTIMATE IN HOURS
					1	Not Started			Not Started		1
					2	In Progress			In Progress		2
					8	Completed			Completed		4
					8	Not Started					8
					4					16
					80					24
					16					40
					8					80
					4
					2
					24
					40
					8

## User_Stories_or_Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE	TASK DESCRIPTION	ADDED BY	DATED ADDED